## Slide 1
Notes: C3PO
Clif confirmed there is still some serum samples available.
We are trying to get an inventory of microliters available by subject and for how many subjects.
Reach out to Cliff Calliway or Fred Korely if you are interested.
There is not currently any funding available for assays.

## Slide 2: KESETT
64 leadership approved sites
  2 sites have direct contracts with UVA (Children’s National and UVA)
  62 sites / 35 UM contracts are anticipated
UM Contract Status: 33 Contracts / 58 sites
15 active contracts applied to 32 sites.
14 draft agreements are pending site PE and return to MI.
4 are in process and soon to leave Michigan.​
Contract Extensions to extend the current budget year from 7/31 to 12/31 are coming.
​
Subrecipient forms pending return to MI: (2 subrecipient forms / 4 sites)
Columbia​
UCSD (3 - sites)​
​

## Slide 3: KESETT
News
FDA - The FDA has lifted the clinical hold on KESETT.
CIRB Submission - Protocol Approved
DSMB Review - Recommended study proceed
Investigator meeting
10/15 - Travel day with no official study meetings
10/16 - Full day of study meetings
10/17 - Morning meetings with conclusion around noon
All site call - Recording available on the website - Next call in september
KESETT Website https://siren.network/trial/kesett/ or KESETT.org
Draft Protocol, Working MoP, and Working Pharmacy Manual available
Updated “Getting Started” page and relevant materials/instructions
Office hours available Thursdays, noon - 2:00 pm (Eastern), sign up available on the website

## Slide 4: KESETT
Site IRB approval
ICF - Consent forms follow SIRENS locked down consent guidelines. If your IRB requires site specific language please send it to the CCC team as soon as possible for review. This language will be inserted to the consent form before the signature page. Please do make alterations to the IFCs.
FDA and Drug - Drug product labels are being posted to the website if needed for your local approvals. Product labels replace the investigator brochure for sponsor-investigator INDs. FDA release of clinical hold is currently posted.
Ceribell - Resources are available in the workbench if needed for your site submissions
CIRB Site submission - The CCC will complete you Advarra application
EFIC Plan - Available on the study website under ‘EFIC’. CIRB Approved EFIC materials will also be posted

## Slide 5: KESETT
Site submitted questions
  Will Regulatory templates be provided (1572, COI, etc.)? If so, where will be able to find them.
    1572 will be going out tomorrow or thursday to sites. COI forms are not applicable to site level teams and investigators.
      Additionally with the 1572 we will be sending the site checklist with tasks and documents needed to complete start-up.
  Will subjects be receiving payment for participating in this study? Please elaborate on this.
    Subjects/participants will not be receiving be receiving payment for the study. The focus group attendees will be compensated by UAB, however as they are not to study participants this is not considered participant payment in our IRB application. The EFIC plan includes these payments which was reviewed and approved by the CIRB.
  A google doc alternative for study documents is still in the works, with a mirrored dropbox being the most probable solution

## Slide 6: Updated Site Timeline
August
September
October
November
EFIC
IRB
Ceribell
WebDCU
Local Event 1
Obtain Local IRB approval
Ceribell IT approval
Ceribell Training
Local Event 2
Focus Group 1
Focus Group 2
eDOA
EFIC Context
EFIC CC Event forms
CIRB Application
Form
Upload Regulatory Documents
Today
8/8
8/1
9/30
CCC submits CIRB application
EFIC Public Disclosure UAB (60 days)

## Slide 7: KESETT
Ceribell - Has begun contacting select sites for 30 minute introduction meetings, more will be contacted as contracts return
Ceribell device overview
Discuss Ceribell at your site currently
Site specific Considerations
Before Site meeting work to identify:
Review Ceribell Implementation Guide for Sites on the Website in the ‘Workbench’
Ceribell use at the site
  Not approved for any use
  Approved for clinical use - Where is it being implemented, ED?
  Approved for research - Does this conflict with another study?
Consider Who will be applying the Ceribell device? (Nurse, Tech, ED Provider, SC if available)
Other site barriers
If your site uses Ceribell in the ED routinely for Status epilepticus patients
Confirm with the CCC if and how the research recorder will be implemented at your site.

## Slide 8: KESETT
PK-PD Study – Ancillary study all sites should plan to participate in
Will be included in the EFIC activities with the main study and main consent
All participants are eligible if they can provide a blood draw
Two blood samples (2-3 mL/sample)
  5-45 min after start of drug infusion
  60-120 min after start of drug infusion
Spin and separate within 2 hours of collection
Ship individually or batched, whichever works best for your site
Store cryogenic vials and vacutainer tubes at -20°C or lower
This ancillary study will have its own funds, you do not need to budget or accrue any lab related fees prior to the ancillary being awarded. However, it would be best to plan to have blood draws ready to be added to your enrollment workflow.

## Slide 9: KESETT
WebDCUv2
KESETT regulatory database released, eDOAs available to be completed
KESETT is in WebDCUv2 which is a different site than current and previous SIREN trials
If anyone who will be helping with setting up the DOA or uploading regulatory documents doesn't have access, please reach out to me at luckmann@musc.edu
If anyone if having issues with access, also feel free to reach out.
Once your eDOA has been reviewed and approved your requested regulatory documents will populate.
The WebDCU User Resources - Located on the ‘Getting Started’ page of the KESETT website
  SIREN WebDCU V2.1 User Manual also included in the start up email, contains guidance on setting up DOAs/uploading reg docs
  KESETT Regulatory Document Approval Parameters document has specifics on eDOA completion and document uploads.

## Slide 10: KESETT
WebDCU Forms Needed
eDOA - As soon as possible
  Please follow the guidance for required responsibilities listed in the regulatory parameters doc
  Please include your Hub PI and Hub project manager on your eDOA, there are specific roles for them. If you are not sure who this is please email me
  Provide a single PSC
  Headband tracking should be limited to 1-2 team members
  Responsibilities of Drug tracking and maintenance ‘Responsibility-I’ are reserved for the pharmacy roles.
EFIC Plan - cIRB approved
CC/PD Materials - cIRB approved
Milestones
Local context form - end of the week (8/8)
CC/PD Forms
Centralized EFIC activities with UAB

## Slide 11: KESETT - EFIC
Same
Regulations
Goals and mindset remain value-added, investigator engaged
Community Consultation
Public Disclosure
New
Hybrid - Site/Centralized approach coordinated at University of Alabama (UAB)
What to do at your site
2 virtual focus groups moderated by UAB
  You will be asked to recruit about 8 stakeholders of differing perspectives for these groups. You can identify from where you may recruit these locally.
2 in-person events
  Over the summer these may be fairs, festivals, markets, epilepsy strolls or other community events. Look at your community calendar and think about what you might do.
Review and share any new local institutional processes/policy
If you have an local event occurring in July that you would like to attend please contact the KESETT team
EFIC plan and CC/PD materials under IRB review and will be released as soon as they are approved

## Slide 12: KESETT Questions?
KESETT Website:
https://siren.network/Clinical-trials/kesett
KESETT CCC contact:
kesett-contact@umich.edu
KESETT contract questions:
kesett-contract@umich.edu
KESETT “Office Hours”
Every Thursday sign up under the “Workbench” tab to meet with the KESETT Site Manager, HSP Specialist, and Project Manager.