## Slide 1
Notes: C3PO
Clif confirmed there is still some serum samples available.
We are trying to get an inventory of microliters available by subject and for how many subjects.
Reach out to Cliff Calliway or Fred Korely if you are interested.
There is not currently any funding available for assays.

## Slide 2: KESETT
64 leadership approved sites
  2 sites have direct contracts with UVA (Children’s National and UVA)
  62 sites / 34 UM contracts are anticipated
UM Contract Status: 34 Contracts / 62 sites
25 active contracts applied to 45 sites.
        Hub-spoke agreements - in progress
9 draft agreements are pending site PE and return to MI.
Site Contract Extension through 12/31 were requested and have all left UM.
​

## Slide 3: KESETT - News
CIRB
Facilitator guide and slides reviewed today
Protocol v2 Modification With Advarra
Investigator meeting - New Orleans 10/16 - 10/17 - See you soon!
‘Stories from the trenches’ - Volunteers requested
UAB Kick-off 10/16
Email siren-travel@umich.edu for questions or additional team members traveling on site funds.
Doubletree on Canal Street
  DO NOT CONTACT HOTEL DIRECTLY
Updates
FAQ section coming soon from all site call questions
No All-site call in October due to IM
KESETT Website https://siren.network/trial/kesett/ or KESETT.org
Draft Protocol, Working MoP, and Working Pharmacy Manual available
Updated “Getting Started” page and relevant materials/instructions
Office hours available Thursdays, noon - 2:00 pm (Eastern), sign up available on the website

## Slide 4: Local IRB Submission
Site IRB approval - Advarra requires documentation from your site IRB acknowledging agreement of Advarra serving as the approving IRB for your site.
ICF - Consent forms follow SIRENS locked down consent guidelines. If your IRB requires site specific language please send it to the CCC team as soon as possible for review. This language will be inserted to the consent form before the signature page. Please do make alterations to the IFCs.
FDA and Drug - Drug product labels are posted to the website if needed for your local approvals. Product labels replace the investigator brochure for sponsor-investigator INDs. FDA release of clinical hold is currently posted.
Ceribell - Resources are available in the workbench
Advarra CIRB approval - Approval letters from CIRB posted in the Workbench
CIRB Site submission - The CCC will complete you Advarra application
EFIC - Plan Available on the study website under ‘EFIC’. CIRB Approved EFIC materials will also be posted here

## Slide 5: Sample Site Timeline
August
September
October
November
EFIC
IRB
Ceribell
WebDCU
Local Event 1
Obtain Local IRB Ceding approval
Ceribell IT approval
Ceribell Training
Local Event 2
Focus Group 2
Focus Group 1
eDOA
EFIC Context
EFIC CC Event forms
CIRB Application
Form
Upload Regulatory Documents
8/8
8/1
CCC submits CIRB application
EFIC Public Disclosure UAB (60 days)

## Slide 6: KESETT
Ceribell - Megan Wardius will be reaching out to site that have not completed a Ceribell intake call to update on where you are in the process and determine if a call with Ceribell would be beneficial.
Ceribell reps will be present at the IM for questions and to get hands on with the device
IT Approval - This can be a long process. Ensure you are beginning this process now.
Review Ceribell Implementation Guide for Sites on the Website in the ‘Workbench’
Consider Who will be applying the Ceribell device? (Nurse, Tech, ED Provider, SC if available)
Ceribell ED use
Identify if Ceribell is routinely for Status epilepticus patients in the ED
Confirm with the CCC if and how the research recorder will be implemented at your site.

## Slide 7: KESETT
PK-PD Study – Ancillary study all sites should plan to participate in
Will be included in the EFIC activities with the main study and main consent
All participants are eligible if they can provide a blood draw
Two blood samples (2-3 mL/sample)
  5-45 min after start of drug infusion
  60-120 min after start of drug infusion
Spin and separate within 2 hours of collection
Ship individually or batched, whichever works best for your site
Store cryogenic vials and vacutainer tubes at -20°C or lower
This ancillary study will have its own funds, you do not need to budget or accrue any lab related fees prior to the ancillary being awarded. However, it would be best to plan to have blood draws ready to be added to your enrollment workflow.

## Slide 8: KESETT - WebDCUv2
WebDCUv2
KESETT is in WebDCUv2 which is a different site than current and previous SIREN trials
If anyone who will be helping with setting up the DOA or uploading regulatory documents doesn't have access, or is having issues with access, please reach out to Riley Luckmann <luckmann@musc.edu>
Once your eDOA has been reviewed and approved your requested regulatory documents will populate.
Site CIRB application form coming soon
Site Addresses
  Mailing address
  Investigational product shipping address
  EFIC material shipping address
  Headband and device shipping address
The WebDCU User Resources - Located on the ‘Getting Started’ page of the KESETT website and in the workbench
  SIREN WebDCU V2.1 User Manual contains guidance on setting up DOAs/uploading reg docs
  KESETT Regulatory Document Approval Parameters document has specifics on eDOA completion and document uploads.

## Slide 9: KESETT
WebDCU Forms Needed
eDOA - As soon as possible
  Please follow the guidance for required responsibilities listed in the regulatory parameters doc
  Please include your Hub PI and Hub project manager on your eDOA, there are specific roles for them. If you are not sure who this is please email me
  Provide a single PSC and PI
  Headband tracking should be limited to 1-2 team members
  Responsibilities of Drug tracking and maintenance ‘Responsibility-I’ are reserved for the pharmacy roles.
Local context form - As soon as possible
  Needed to start your PD activities through UAB. You will be contacted for a Kick-off meeting once we have this and your executed contract

## Slide 10: KESETT - Reminders
eDOA submissions
  Detroit Receiving Hospital & Sinai Grace
  VCU Medical Center
  Medical University of South Carolina University Hospital
  Jefferson Einstein Philadelphia Hospital
  University Medical Center New Orleans
  Orlando Regional Medical Center
  Parkland Memorial Hospital
Local Context Form
  Children's Hospital of Wisconsin
  Froedtert Hospital
  Medical University of South Carolina University Hospital
  Orlando Regional Medical Center
  OSU Wexner Medical Center
  UCSD Medical Center / Hillcrest Hospital / La Jolla
  University Medical Center New Orleans
  VCU Medical Center

## Slide 11: KESETT - EFIC
Same
Regulations
Goals and mindset remain value-added, investigator engaged
Community Consultation
Public Disclosure
New
Hybrid - Site/Centralized approach coordinated at University of Alabama (UAB)
What to do at your site
2 virtual focus groups moderated by UAB
  You will be asked to recruit about 8 stakeholders of differing perspectives for these groups. You can identify from where you may recruit these locally.
  Conducted after UAB Kick-off
2 in-person events
  Fairs, festivals, markets, epilepsy strolls or other community events. Look at your community calendar and think about what you might do.
  PI participation required
  Sites in the same geographic catchment area are encouraged to collaborate
Review and share any new local institutional processes/policy
EFIC plan and CC/PD materials cIRB approved - more to come soon

## Slide 12: KESETT - EFIC Things to explore/plan now:
EFIC Kick-off Call - UAB will reach out to schedule your initiation call. Please respond promptly with availability. The timeline for the PD activity is 60 days, which will not start until the call takes place. Please be reaching out to local stakeholders in advance, so that focus groups can be scheduled.
Focus groups - Identify where to potentially recruit about 8 stakeholders of differing perspectives for each focus group session. These should be completed by the end of your PD window.
Local Community Consultation - Identify events, fairs, festivals, markets, epilepsy strolls or other community events. Look at your community calendar
Public Disclosure - Think about important neighbourhoods for focused disclosures

## Slide 13: KESETT Questions?
KESETT Website:
https://siren.network/Clinical-trials/kesett
KESETT CCC contact:
kesett-contact@umich.edu
KESETT contract questions:
kesett-contract@umich.edu
KESETT “Office Hours”
Every Thursday sign up under the “Workbench” tab to meet with the KESETT Site Manager, HSP Specialist, and Project Manager.