## Slide 1
Notes: C3PO
Clif confirmed there is still some serum samples available.
We are trying to get an inventory of microliters available by subject and for how many subjects.
Reach out to Cliff Calliway or Fred Korely if you are interested.
There is not currently any funding available for assays.

## Slide 2: KESETT - Contracts & Invoices
68 leadership approved sites
UM Contract Status: 34 Contracts
30 active
        SIREN Hub-spoke agreement - reminder
4 Pending: HFHS, ILL, Nationwide, UCSD
​
Invoicing
  Generated for November
  Please work with Erin and Vince if you have any questions related tasks associated with Start-up payment 1

## Slide 3: KESETT - News
CIRB
1st sites planned to submit to Advarra 12/15 (UVA, Temple, Yale, Harborview)
Investigator meeting
Trainings from the IM are posted on the KESETT Website
  Please refer to your people regulatory documents page for required trainings per roles
Updates
FAQ Posting on the website. This is a living document and will be updated as items need
Data collection guidelines posted
Mock enrollment video posted
Next all site call 12/5
  Site readiness tasks
  Clinical team training
  EFIC/focus groups & open discussion
  Open questions
KESETT Website https://siren.network/trial/kesett/ or KESETT.org
Home for documents and trainings
Office hours available Thursdays, noon - 2:00 pm (Eastern), sign up available on the website

## Slide 4: Local IRB Submission
ICF - Consent forms follow SIRENS locked down consent guidelines. If your IRB requires site specific language please send it to the CCC team as soon as possible for review. This language will be inserted to the consent form before the signature page. Please do not make alterations to the IFCs.
FDA and Drug - Drug product labels are posted to the website if needed for your local approvals. Product labels replace the investigator brochure for sponsor-investigator INDs. FDA release of clinical hold is currently posted.
Ceribell - Resources are available in the workbench
Advarra CIRB approval - Approval letters from CIRB posted in the Workbench
CIRB Site submission - The CCC will complete you Advarra application
EFIC - Plan Available on the study website under ‘EFIC’. CIRB Approved EFIC materials will also be posted here

## Slide 5: Sample Site Timeline
September
October
November
December
EFIC
IRB
Ceribell
WebDCU
Local Event 1
Obtain Local IRB Ceding approval
Ceribell IT approval
Ceribell Training
Local Event 2
Focus Group 2
Focus Group 1
EFIC CC Event forms
CIRB Application
Form
Upload Regulatory Documents
CIRB app (CCC)
EFIC Public Disclosure with UAB (60 days)
Readiness Call
Enrollment
Release to Enroll
Report Ready
eDOA
Local Context

## Slide 6: KESETT - Ceribell
Ceribell
Reach out if you would like to schedule a call with the Ceribell team and discuss the device at your site
We can assist in facilitating on site trainings as your team approaches release for enrollment
IT Approval - This can be a long process. Ensure you are beginning this process now.
Review Ceribell Implementation Guide for Sites on the Website in the ‘Workbench’
Identify who will be applying the Ceribell device? (Nurse, Tech, ED Provider, SC if available)
Ceribell ED use
Identify if Ceribell is routinely for Status epilepticus patients in the ED
Confirm with the CCC if and how the research recorder will be implemented at your site.

## Slide 7: KESETT - PK/PD (KPOP)
PK-PD Study – Ancillary study all sites should plan to participate in
Will be included in the EFIC activities with the main study and main consent
All participants are eligible if they can provide a blood draw
Two blood samples (2-3 mL/sample)
  5-45 min after start of drug infusion
  60-120 min after start of drug infusion
Spin and separate within 2 hours of collection
Ship individually or batched, whichever works best for your site
Store cryogenic vials and vacutainer tubes at -20°C or lower
This ancillary study will have its own funds, you do not need to budget or accrue any lab related fees prior to the ancillary being awarded. However, it would be best to plan to have blood draws ready to be added to your enrollment workflow.

## Slide 8: KESETT - WebDCU
Please upload all documents in PDF format
Access for uploading regulatory document issues with access, please reach out to Riley Luckmann <luckmann@musc.edu>
Once your eDOA has been reviewed and approved your requested regulatory documents will populate
Site Addresses
Mailing address
Investigational product shipping address
EFIC material shipping address
Headband and device shipping address
CIRB Tables
Site overview - Please complete or review this form available on WebDCU Version1. You may receive an email from the DCC to log onto version 1 and reset your password for access.
Site Regulatory Inspection History - Also available in WebDCU Version1. Please review for accuracy and update with any new inspections.
Initial Site Submission - Found on the KESETT Central IRB tab in WebDCU Version 2. Please fill out your site information which is needed for your CIRB application.

## Slide 9: KESETT - Training
Protocol – IM video and quiz on the Website > Upload quiz results to WebDCU
Data – IM video on the Website > Upload cert to WebDCU
Regulatory – IM Video on the Website > Upload cert to WebDCU
  Required for KESETT as WebDCUv2 has some new features
Pharmacy – Have pharmacists on the eDOA review the pharmacy manual and sign the attestation on the website > Upload attestation to WebDCU
Clinical – Attestation by the site PI (protocol signature page) > Upload to WebDCU

## Slide 10: KESETT - Reminders
eDOA submissions missing or pending edits
  Children's of Alabama
  Emory University Hospital
  Hospital of the University of Pennsylvania
  Kings County Hospital Center
  Medical University of South Carolina University Hospital
  Orlando Regional Medical Center
  University Medical Center New Orleans
Local Context Form Missing
  Medical University of South Carolina University Hospital
  Orlando Regional Medical Center
  University Medical Center New Orleans

## Slide 11: Local IRB Acknowledgement Received
Children's Hospital Los Angeles
Harborview Medical Center
Johns Hopkins Hospital
Northwestern Memorial Hospital
Oregon Health & Science University Hospital
OSU Wexner Medical Center
Reading Hospital
Ronald Reagan UCLA Medical Center
Rush University Medical Center
Stanford University Medical Center
Temple University Hospital
UC Davis Medical Center
University of Michigan University Hospital
University of New Mexico Hospital
UPMC Presbyterian Hospital
UVA Medical Center
Yale New Haven Hospital

## Slide 12: KESETT - EFIC
Same
Regulations
Goals and mindset remain value-added, investigator engaged
Community Consultation
Public Disclosure
New
Hybrid - Site/Centralized approach coordinated at University of Alabama (UAB)
What to do at your site
2 virtual focus groups moderated by UAB
  You will be asked to recruit about 8 stakeholders of differing perspectives for these groups. You can identify from where you may recruit these locally.
  Conducted after UAB Kick-off
  Investigators and study team are requested to be on this call. Please select one team member to lead for the study team.
2 in-person events
  Fairs, festivals, markets, epilepsy strolls or other community events. Look at your community calendar and think about what you might do.
  PI participation required
  Sites in the same geographic catchment area are encouraged to collaborate
Review and share any new local institutional processes/policy
EFIC plan and CC/PD materials cIRB approved - more to come soon

## Slide 13: KESETT - EFIC Things to explore/plan now:
EFIC Kick-off Call - UAB will reach out to schedule your initiation call. Please respond promptly with availability. The timeline for the PD activity is 60 days, which will not start until the call takes place. Please be reaching out to local stakeholders in advance, so that focus groups can be scheduled.
Focus groups - Identify where to potentially recruit about 8 stakeholders of differing perspectives for each focus group session. These should be completed by the end of your PD window.
Local Community Consultation - Identify events, fairs, festivals, markets, epilepsy strolls or other community events. Look at your community calendar
Public Disclosure - Think about important neighbourhoods for focused disclosures

## Slide 14: KESETT Questions?
KESETT Website:
https://siren.network/Clinical-trials/kesett
KESETT CCC contact:
kesett-contact@umich.edu
KESETT contract questions:
kesett-contract@umich.edu
KESETT “Office Hours”
Every Thursday sign up under the “Workbench” tab to meet with the KESETT Site Manager, HSP Specialist, and Project Manager.